This Project is part financed by the European Union Community Initiative INTERREG

INTERREG IIIA project „Business meets culture in Setomaa”

Name of the project:

“Development and promotion of the entrepreneurship in Setomaa based on local cultural traditions”

Partners:

The Union of Setomaa Rural Municipalities and Administration of Pechory District

Objectives of the project:

Overall objective: to develop entrepreneurship in Setomaa based on local cultural traditions.

The project is mainly a training project, which should promote the entrepreneurship in Setomaa related to handicraft. The trainings are targeted to the individuals, who are willing to combine the handicraft with business and wish to earn a living using handicraft skills.

Other objectives:

- To map the current situation of traditional handicraft skills in Setomaa

- To organize 16-days business training for 20 persons, who will get basic knowledge about starting a business

- To organize handicraft training for 20 persons, who wish to earn a using with handicraft skills

- To arrange the participation of the trainees in master-classes in Lindora, Izborsk and Pechory fairs and to publish the promotional material

- To arrange the summer-schools for youth and children about Seto traditional handicraft

- To establish networks between handicraft masters and businessmen in East-Pechory and West-Setomaa

The financers of the project:

EU initiative INTERREG, Estonian Ministry of the Interior, The Union of Setomaa Rural Municipalities

Time schedule:

1. Preparation of the activities, promotion: February – September 2006

2. The research about the handicraft skills and masters: June – September 2006

3. The selection of the handicraft skills and masters: July – September 2006

4. Applications from candidates for the business training: June-July 2006

5. The selection of mentors for business training: June-July 2006

6. Applications from candidates for the handicraft training: July-September 2006

7. The training for mentors: August 2006

8. Business training: September 2006 – May 2007

9. Handicraft training: October 2006 – March 2007

10. Master classes in Izborsk fair: July 2006, June 2007

11. Master classes in Pechory fair: August 2006 and 2007

12. Master classes in Lindora fair: October 2006 and 2007

13. Summer-school for children and youth: August 2006 and 2007

14. Sum up and arrangement of the closing seminars: September – December 2007